## Guide
VIXIV LTD — Generic flip programme (deal secured → sale completed)
HOW TO USE
1. Open a Deal tab. Fill the yellow cells: deal name, route (Auction / Estate agent), deal secured date, contractor.
2. Set the scope switches (Y/N). Activities switched off grey out and take no time; their successors close up automatically.
3. Replace the default durations (yellow, working days) with your builder's programme once you have it.
4. Read the Flags column and Key Dates. Hold points (yellow rows) are go/no-go decisions — do not pass them without a decision.
5. The Pipeline tab compares Deal 1 and Deal 2 and flags if both builds need the crew at the same time.
6. Update Status as work progresses. To start a new deal, copy a Deal tab (right-click → Move or Copy → Create a copy).
SCHEDULING LOGIC
• All durations are WORKING days (Mon–Fri) and skip every date on the Holidays tab.
• FS = finish-to-start: starts the working day after the predecessor finishes, plus any lag.
• SS = start-to-start: starts with the predecessor, plus the lag in working days.
• Construction activities (Contingency = Y) are lengthened by the contingency % in C10, rounded up.
• Plaster drying gets extra days automatically when it starts between November and February (C11).
• Auction completion = deal date + 28 calendar days (C8), moved to the next working day if needed.
• Construction sequence: strip-out → opening-up hold → structure / damp / roof / windows → first fix (electrics, plumbing, joinery in parallel) → first-fix check → plaster → drying → mist coat → kitchen + bathroom → second fix → decoration → flooring → snag → practical completion.
ASSUMPTIONS (illustrative — verify)
• Default durations suit a 2–3 bed terrace cosmetic-plus refurb (about 9–11 weeks on site). Replace with your builder's figures.
• Sale agreed in about 6 weeks after listing; sale agreed → completion about 12–14 weeks. Market dependent.
• Bank holidays for England & Wales are computed by formula for 2026–2028 — verify at gov.uk/bank-holidays.
• Asbestos survey, EPC before marketing, CIS, and certificate requirements: confirm with your solicitor, accountant and contractor.
COLOUR CODE
Yellow cell + blue text = input you edit. Black = formula. Green text = link from another tab. Red text = flag.

## Pipeline
Pipeline — two overlapping flips
Pulls key dates from Deal 1 and Deal 2. The crew check flags if both builds run at once. To add Deal 3: copy a deal tab and add a column here.
| Deal 1 | Deal 2
Deal | EXAMPLE — 2-bed terrace, Rochdale (replace) | EXAMPLE — 3-bed semi via agent (replace)
Route | Auction | Estate agent
Lead contractor | Mentor's crew (TBC) | Friend (general builder)
Deal secured | 2026-12-10 | 2027-02-01
Purchase completion | 2027-01-07 | 2027-03-31
Works start | 2027-01-15 | 2027-04-08
Practical completion | 2027-04-08 | 2027-06-25
Listed | 2027-04-13 | 2027-06-30
Sale completed | 2027-08-06 | 2027-10-22
Months owned | 6.9317 | 6.7346
Bridge headroom (months) | 5.0683 | 5.2654
Crew clash check | ✓ No build overlap: one crew can run both back-to-back
Capital overlap (both owned at once, days) | 186 | Days both purchases are funded at the same time — check against the £50k pool.
Phase timeline (weekly) |  |  | Dec 26 |  |  |  | Jan 27 |  |  |  | Feb 27 |  |  |  | Mar 27 |  |  |  |  | Apr 27 |  |  |  | May 27 |  |  |  |  | Jun 27 |  |  |  | Jul 27 |  |  |  | Aug 27 |  |  |  |  | Sep 27 |  |  |  | Oct 27 |  |  |  | Nov 27 |  |  |  |  | Dec 27 |  |  |  | Jan 28 |  |  |  |  | Feb 28 |  |  |  | Mar 28 |  |  |  | Apr 28 |  |  |  | May 28
| Start | End | 2026-12-07 | 2026-12-14 | 2026-12-21 | 2026-12-28 | 2027-01-04 | 2027-01-11 | 2027-01-18 | 2027-01-25 | 2027-02-01 | 2027-02-08 | 2027-02-15 | 2027-02-22 | 2027-03-01 | 2027-03-08 | 2027-03-15 | 2027-03-22 | 2027-03-29 | 2027-04-05 | 2027-04-12 | 2027-04-19 | 2027-04-26 | 2027-05-03 | 2027-05-10 | 2027-05-17 | 2027-05-24 | 2027-05-31 | 2027-06-07 | 2027-06-14 | 2027-06-21 | 2027-06-28 | 2027-07-05 | 2027-07-12 | 2027-07-19 | 2027-07-26 | 2027-08-02 | 2027-08-09 | 2027-08-16 | 2027-08-23 | 2027-08-30 | 2027-09-06 | 2027-09-13 | 2027-09-20 | 2027-09-27 | 2027-10-04 | 2027-10-11 | 2027-10-18 | 2027-10-25 | 2027-11-01 | 2027-11-08 | 2027-11-15 | 2027-11-22 | 2027-11-29 | 2027-12-06 | 2027-12-13 | 2027-12-20 | 2027-12-27 | 2028-01-03 | 2028-01-10 | 2028-01-17 | 2028-01-24 | 2028-01-31 | 2028-02-07 | 2028-02-14 | 2028-02-21 | 2028-02-28 | 2028-03-06 | 2028-03-13 | 2028-03-20 | 2028-03-27 | 2028-04-03 | 2028-04-10 | 2028-04-17 | 2028-04-24 | 2028-05-01 | 2028-05-08 | 2028-05-15 | 2028-05-22 | 2028-05-29
Deal 1 — Legal | 2026-12-10 | 2027-01-07
Deal 1 — Build | 2027-01-15 | 2027-04-08
Deal 1 — Sale | 2027-04-13 | 2027-08-06
Deal 2 — Legal | 2027-02-01 | 2027-03-31
Deal 2 — Build | 2027-04-08 | 2027-06-25
Deal 2 — Sale | 2027-06-30 | 2027-10-22

## DD Checklist
Default due-diligence checklist
Stage 1 is done BEFORE bidding (auction) or before the offer is final (agent). Programme ID links each later check to its activity.
# | Stage | Check | Why it matters / what good looks like | Programme ID | Done (Y/N) | Notes
1 | 1 Before bid / offer | Read the full legal pack with your solicitor | Title, searches, special conditions, completion period, extra fees the buyer pays. | A7
2 | 1 Before bid / offer | Check special conditions for hidden costs | Seller's legal fees, search fees, arrears, VAT — add all to the appraisal. | —
3 | 1 Before bid / offer | Why is it at auction / why is it cheap? | Unmortgageable, probate, repossession, structural defect, short lease, sitting tenant. | —
4 | 1 Before bid / offer | View with the builder; photos and video | Builder's schedule of works and price range before you bid. | B1
5 | 1 Before bid / offer | Three or more sold comparables (same street/type, last 12 months) | Set the WORST-CASE end value (training rule). | —
6 | 1 Before bid / offer | DealsDash appraisal: max bid incl. SDLT, fees, buyer's premium | Profit first; stress tests and walk-away tests pass. | —
7 | 1 Before bid / offer | Construction type and end-buyer mortgageability | Non-standard construction or defects can kill the resale. Your buyer needs a mortgage. | —
8 | 1 Before bid / offer | Mining, flood, knotweed, conservation area, planning history | Rochdale is a former coalfield: check the Coal Authority report. | —
9 | 1 Before bid / offer | Tenure and occupancy | Freehold vs leasehold terms; vacant possession confirmed. | —
10 | 1 Before bid / offer | Bridging decision in principle; lender can complete within 28 days | No DIP = no bid. | A5
11 | 1 Before bid / offer | Deposit (10%) + fees available on the day; insurance quote ready | Bind insurance at the hammer. | A2
12 | 1 Before bid / offer | Set the absolute maximum bid and walk away above it | Write it down before the auction starts. | —
13 | 2 After deal secured | Insurance bound; solicitor and lender instructed | Same day for auction. | A2
14 | 2 After deal secured | Agent route: searches, survey and title reviewed | Renegotiate or withdraw at the hold point. | A9
15 | 2 After deal secured | Contractor contract signed; insurance seen; CIS verified | Fixed price by stage, 5% retention. | B3
16 | 2 After deal secured | Asbestos survey (pre-2000) before strip-out |  | B6
17 | 3 During works | Opening-up review: costs updated in DealsDash | Hidden defects found here; re-check profit. | C2
18 | 3 During works | First-fix photos before boarding | Proof for certificates and future buyers. | D4
19 | 4 Before listing | All certificates collected (EIC, Gas Safe, FENSA, Building Control, damp guarantee) | Buyer's solicitor will ask. | G1
20 | 4 Before listing | EPC commissioned | Must be commissioned before marketing. | G4
21 | 4 Before listing | Three agent valuations vs your worst-case end value | Price realistically from day one. | H1
22 | 5 Sale | Sale progression chased weekly | Most delays are paperwork. | H5
23 | 5 Sale | Bridge redemption statement requested two weeks before completion | No surprise interest or fees. | H7
24 | 5 Sale | Close-out: actual vs appraised profit and durations | Update this template's default durations. | H9

## Deal 1
VIXIV LTD — Flip programme: Deal 1
Edit only the YELLOW cells (blue text). Dates, Gantt and flags recalculate. Durations are working days. Example values shown — replace with your deal.
| DEAL INPUTS |  |  | SCOPE SWITCHES (Y/N) |  |  | KEY DATES (calculated)
| Deal name / address | EXAMPLE — 2-bed terrace, Rochdale (replace) |  | Pre-2000 build | Y |  | Purchase completion | 2027-01-07
| Purchase route | Auction |  | Structural | N |  | Works start (strip-out) | 2027-01-15
| Deal secured date | 2026-12-10 |  | Damp/timber | Y |  | Practical completion | 2027-04-08
| Auction completion period (calendar days) | 28 |  | Roof/external | N |  | Listed | 2027-04-13
| Agent route: exchange → completion (WD) | 10 |  | Windows/doors | N |  | Sale agreed | 2027-05-26
| Contingency on construction durations | 15% |  | Rewire | Y |  | Sale completed | 2027-08-06
| Winter drying allowance (extra WD, Nov–Feb) | 3 |  | Heating/boiler | Y |  | Build duration (WD) | 58
| WD to agree a sale after listing | 30 |  | Kitchen | Y |  | Months owned (completion → sale) | 6.9317
| Bridge term (months) | 12 |  | Bathroom | Y |  | Bridge headroom (months) | 5.0683
| Lead contractor | Mentor's crew (TBC) |  |  |  |  | Deal secured → sale completed (days) | 239
| Sale: exchange → completion (WD) | 10
| Gantt key: | A Purchase & DD | B Pre-start | C Strip-out & structure | D First fix | E Plaster | F Second fix & finish | G Sign-off | H Sale & close-out | ■ milestone
[19 empty] | Dec 26 |  |  |  | Jan 27 |  |  |  | Feb 27 |  |  |  | Mar 27 |  |  |  |  | Apr 27 |  |  |  | May 27 |  |  |  |  | Jun 27 |  |  |  | Jul 27 |  |  |  | Aug 27 |  |  |  |  | Sep 27 |  |  |  | Oct 27 |  |  |  | Nov 27 |  |  |  |  | Dec 27 |  |  |  | Jan 28
ID | Phase | Activity | Owner | Route | Scope switch | Hold point | Dur WD (auction) | Dur WD (agent) | Contingency? | Applies? | Dur used (WD) | Predecessors | Lag (WD) | Start | Finish | Status | Flags | Notes / what good looks like | time axis 2026-12-07 to 2028-01-24
A1 | A Purchase & DD | Deal secured (auction: hammer falls = exchange; agent: offer accepted) | Paul | Both |  |  | 0 | 0 | N | Y | 0 | — | 0 | 2026-12-10 | 2026-12-10 | Not started |  | Day 0. Everything else is driven from the date in C7.
A2 | A Purchase & DD | Buildings insurance (unoccupied cover) in force | Paul / broker | Both |  |  | 1 | 1 | N | Y | 1 | A1SS | 0 | 2026-12-10 | 2026-12-10 | Not started |  | Auction: risk passes to you at the hammer. Agent route: must be on cover from exchange at the latest.
A3 | A Purchase & DD | Pay 10% deposit + buyer's premium / auction fees | Paul | Auction |  |  | 1 | 0 | N | Y | 1 | A1SS | 0 | 2026-12-10 | 2026-12-10 | Not started |  | Paid on the day. Funds must be ready before you bid.
A4 | A Purchase & DD | Instruct solicitor; legal pack / memorandum of sale to solicitor and lender | Paul | Both |  |  | 2 | 2 | N | Y | 2 | A1SS | 0 | 2026-12-10 | 2026-12-11 | Not started
A5 | A Purchase & DD | Bridging valuation instructed and inspection done | Broker / lender | Both |  |  | 5 | 5 | N | Y | 5 | A4SS | 1 | 2026-12-11 | 2026-12-17 | Not started |  | Ideally have a decision in principle BEFORE the auction.
A6 | A Purchase & DD | Bridging underwriting and formal loan offer | Lender | Both |  |  | 5 | 5 | N | Y | 5 | A5FS | 0 | 2026-12-18 | 2026-12-24 | Not started
A7 | A Purchase & DD | Searches and enquiries raised and answered | Solicitor | Estate agent |  |  | 0 | 25 | N | N | 0 | A4FS | 0 | 2026-12-14 | 2026-12-11 | Not started |  | Auction route: done BEFORE bidding (see DD Checklist).
A8 | A Purchase & DD | Independent survey + builder walk-round for quote | Surveyor / builder | Estate agent |  |  | 0 | 10 | N | N | 0 | A4SS | 2 | 2026-12-14 | 2026-12-11 | Not started
A9 | A Purchase & DD | Review title, searches and survey: renegotiate or withdraw | Paul + mentor | Estate agent |  | HOLD | 0 | 3 | N | N | 0 | A7FS; A8FS | 0 | 2026-12-14 | 2026-12-11 | Not started |  | Re-run the DealsDash appraisal with real costs. Walk away if it fails.
A10 | A Purchase & DD | Exchange contracts (deposit paid) | Solicitor | Estate agent |  |  | 0 | 0 | N | N | 0 | A9FS; A6FS | 0 | 2027-01-04 | 2026-12-24 | Not started |  | Legally committed from here.
A11 | A Purchase & DD | Lender's legal work, report on title, funds requested | Solicitors | Both |  |  | 5 | 5 | N | Y | 5 | A6FS; A10FS | 0 | 2027-01-04 | 2027-01-08 | Not started
A12 | A Purchase & DD | PURCHASE COMPLETION: keys released | Solicitor | Both |  |  | 0 | 0 | N | Y | 0 | A1 (auction) / A10, A11 (agent) | 0 | 2027-01-07 | 2027-01-07 | Not started | ⚠ Finance not ready by auction completion: deposit at risk. | Auction: fixed by contract (usually 28 calendar days). Agent: exchange + C9 working days.
B1 | B Pre-start | Builder schedule of works and measured scope | Builder | Both |  |  | 3 | 3 | N | Y | 3 | A1FS; A8FS | 0 | 2026-12-14 | 2026-12-16 | Not started |  | Auction: arrange access via auctioneer/seller, or use the pre-bid viewing scope.
B2 | B Pre-start | Fixed-price quote(s) received; mentor review | Builder / mentor | Both |  |  | 5 | 5 | N | Y | 5 | B1FS | 0 | 2026-12-17 | 2026-12-23 | Not started
B3 | B Pre-start | Sign contract: scope, stage payments, 5% retention; check insurance, verify CIS | Paul | Both |  | HOLD | 2 | 2 | N | Y | 2 | B2FS | 0 | 2026-12-24 | 2027-01-04 | Not started | ■ HOLD: go/no-go. | No signed scope + price = no start.
B4 | B Pre-start | Order long-lead items (kitchen, boiler, windows) | Paul / builder | Both |  |  | 1 | 1 | N | Y | 1 | B3FS | 0 | 2027-01-05 | 2027-01-05 | Not started
B5 | B Pre-start | Long-lead delivery window | Suppliers | Both |  |  | 15 | 15 | N | Y | 15 | B4FS | 0 | 2027-01-06 | 2027-01-26 | Not started |  | Typical 3 weeks; windows can be 4–6. Edit to supplier quote.
B6 | B Pre-start | Asbestos refurbishment survey | Surveyor | Both | Pre-2000 build |  | 5 | 5 | N | Y | 5 | A12FS | 0 | 2027-01-08 | 2027-01-14 | Not started |  | Before any intrusive work on a pre-2000 property (HSE guidance — confirm with contractor).
B7 | B Pre-start | Utilities and meter readings, council tax, change locks, skip, start photos | Paul | Both |  |  | 1 | 1 | N | Y | 1 | A12FS | 0 | 2027-01-08 | 2027-01-08 | Not started
C1 | C Strip-out & structure | Strip-out: kitchen, bathroom, flooring, blown plaster | Builder | Both |  |  | 4 | 4 | Y | Y | 5 | B7FS; B6FS; B3FS | 0 | 2027-01-15 | 2027-01-21 | Not started
C2 | C Strip-out & structure | Opening-up inspection; update costs in DealsDash | Paul + builder | Both |  | HOLD | 1 | 1 | N | Y | 1 | C1FS | 0 | 2027-01-22 | 2027-01-22 | Not started | ■ HOLD: go/no-go. | Hidden defects show here. Re-check profit vs target before committing more spend.
C3 | C Strip-out & structure | Structural works (engineer design + Building Control notice) | Builder / engineer | Both | Structural |  | 5 | 5 | Y | N | 0 | C2FS | 0 | 2027-01-25 | 2027-01-22 | Not started
C4 | C Strip-out & structure | Damp-proofing / timber treatment | Specialist | Both | Damp/timber |  | 3 | 3 | Y | Y | 4 | C2FS | 0 | 2027-01-25 | 2027-01-28 | Not started |  | Get the guarantee for the sale pack.
C5 | C Strip-out & structure | Roof and external repairs (roof, gutters, pointing, render) | Roofer / builder | Both | Roof/external |  | 8 | 8 | Y | N | 0 | C2FS | 0 | 2027-01-25 | 2027-01-22 | Not started
C6 | C Strip-out & structure | Windows and external doors fitted | Installer | Both | Windows/doors |  | 3 | 3 | Y | N | 0 | C2FS; B5FS | 0 | 2027-01-27 | 2027-01-26 | Not started |  | Keep FENSA certificate.
D1 | D First fix | Electrical first fix (rewire) | Electrician | Both | Rewire |  | 4 | 4 | Y | Y | 5 | C3FS; C4FS | 0 | 2027-01-29 | 2027-02-04 | Not started
D2 | D First fix | Plumbing and heating first fix | Plumber | Both | Heating/boiler |  | 4 | 4 | Y | Y | 5 | C3FS; C4FS | 1 | 2027-02-01 | 2027-02-05 | Not started |  | Starts 1 day after electrics to share the site.
D3 | D First fix | Joinery first fix (stud walls, linings) | Carpenter | Both |  |  | 3 | 3 | Y | Y | 4 | C3FS; C4FS | 0 | 2027-01-29 | 2027-02-03 | Not started
D4 | D First fix | First-fix check before boarding (electrician / Building Control if notifiable) | Builder | Both |  | HOLD | 1 | 1 | N | Y | 1 | D1FS; D2FS; D3FS | 0 | 2027-02-08 | 2027-02-08 | Not started | ■ HOLD: go/no-go. | Photograph every wall before boarding.
E1 | E Plaster | Board, plaster and skim | Plasterer | Both |  |  | 6 | 6 | Y | Y | 7 | D4FS; C5FS; C6FS | 0 | 2027-02-09 | 2027-02-17 | Not started |  | Roof watertight and windows in first.
E2 | E Plaster | Drying out (winter allowance added automatically Nov–Feb) | — | Both |  |  | 5 | 5 | N | Y | 8 | E1FS | 0 | 2027-02-18 | 2027-03-01 | Not started | Winter drying allowance added. | Heat + dehumidifiers. Painting too early = cracking and bloom.
E3 | E Plaster | Mist coat | Decorator | Both |  |  | 2 | 2 | Y | Y | 3 | E2FS | 0 | 2027-03-02 | 2027-03-04 | Not started
F1 | F Second fix & finish | Kitchen fit | Kitchen fitter | Both | Kitchen |  | 4 | 4 | Y | Y | 5 | E3FS; B5FS | 0 | 2027-03-05 | 2027-03-11 | Not started
F2 | F Second fix & finish | Bathroom fit and tiling | Plumber / tiler | Both | Bathroom |  | 5 | 5 | Y | Y | 6 | E3FS | 0 | 2027-03-05 | 2027-03-12 | Not started
F3 | F Second fix & finish | Electrical second fix and testing | Electrician | Both |  |  | 2 | 2 | Y | Y | 3 | F1FS; F2FS | 0 | 2027-03-15 | 2027-03-17 | Not started
F4 | F Second fix & finish | Plumbing / heating second fix; boiler commissioned | Plumber / Gas Safe | Both |  |  | 2 | 2 | Y | Y | 3 | F1FS; F2FS | 0 | 2027-03-15 | 2027-03-17 | Not started
F5 | F Second fix & finish | Joinery second fix (doors, skirting, architrave) | Carpenter | Both |  |  | 3 | 3 | Y | Y | 4 | E3FS | 0 | 2027-03-05 | 2027-03-10 | Not started
F6 | F Second fix & finish | Decoration | Decorator | Both |  |  | 6 | 6 | Y | Y | 7 | F3FS; F4FS; F5FS | 0 | 2027-03-18 | 2027-03-30 | Not started
F7 | F Second fix & finish | Flooring | Flooring fitter | Both |  |  | 2 | 2 | Y | Y | 3 | F6FS | 0 | 2027-03-31 | 2027-04-02 | Not started
F8 | F Second fix & finish | Kerb appeal: front door, paint, garden tidy | Builder | Both |  |  | 2 | 2 | Y | Y | 3 | F6FS | 0 | 2027-03-31 | 2027-04-02 | Not started |  | Training rule: £1 of refurb should add £3 of value.
G1 | G Sign-off | Certificates: EIC (Part P), Gas Safe / Building Regs, FENSA, Building Control completion | Trades | Both |  |  | 3 | 3 | N | Y | 3 | F3FS; F4FS | 0 | 2027-03-18 | 2027-03-22 | Not started |  | Buyer's solicitor will ask for every one. No certs = delayed exchange.
G2 | G Sign-off | Snagging walk-round and fixes | Paul + builder | Both |  |  | 3 | 3 | N | Y | 3 | F7FS; F8FS | 0 | 2027-04-05 | 2027-04-07 | Not started
G3 | G Sign-off | PRACTICAL COMPLETION: stage payment (5% retention held) | Paul | Both |  | HOLD | 0 | 0 | N | Y | 0 | G2FS | 0 | 2027-04-08 | 2027-04-08 | Not started | ■ HOLD: go/no-go. | Sign off only when the snag list is clear.
G4 | G Sign-off | EPC commissioned | Assessor | Both |  |  | 2 | 2 | N | Y | 2 | G2FS | 0 | 2027-04-08 | 2027-04-09 | Not started |  | Must be commissioned before marketing.
G5 | G Sign-off | Deep clean, staging, photos and floorplan | Paul | Both |  |  | 3 | 3 | N | Y | 3 | G2FS | 0 | 2027-04-08 | 2027-04-12 | Not started
H1 | H Sale & close-out | Three agent valuations; instruct agent | Paul | Both |  |  | 3 | 3 | N | Y | 3 | G2SS | 0 | 2027-04-05 | 2027-04-07 | Not started |  | Book during snagging.
H2 | H Sale & close-out | LISTED on portals | Agent | Both |  |  | 0 | 0 | N | Y | 0 | H1FS; G4FS; G5FS | 0 | 2027-04-13 | 2027-04-13 | Not started
H3 | H Sale & close-out | Viewings → sale agreed | Agent | Both |  |  | 30 | 30 | N | Y | 30 | H2FS | 0 | 2027-04-14 | 2027-05-26 | Not started |  | Duration set in C12.
H4 | H Sale & close-out | Memorandum of sale; buyer's mortgage valuation | Agent / buyer | Both |  |  | 10 | 10 | N | Y | 10 | H3FS | 0 | 2027-05-27 | 2027-06-10 | Not started
H5 | H Sale & close-out | Buyer's searches, enquiries and survey; supply certificates | Solicitors | Both |  |  | 40 | 40 | N | Y | 40 | H3FS | 0 | 2027-05-27 | 2027-07-22 | Not started |  | Chase weekly. Typical sale-agreed → completion: 12–16 weeks.
H6 | H Sale & close-out | Exchange contracts on sale | Solicitors | Both |  |  | 0 | 0 | N | Y | 0 | H4FS; H5FS; G1FS | 0 | 2027-07-23 | 2027-07-23 | Not started
H7 | H Sale & close-out | SALE COMPLETION: bridge redeemed | Solicitor | Both |  |  | 0 | 0 | N | Y | 0 | H6FS | 9 | 2027-08-06 | 2027-08-06 | Not started |  | Lag = C15 − 1 so completion lands C15 working days after exchange.
H8 | H Sale & close-out | Retention released (end of defects period) | Paul | Both |  |  | 0 | 0 | N | Y | 0 | G3FS | 60 | 2027-07-06 | 2027-07-06 | Not started |  | Lag 60 WD ≈ 3 months after practical completion.
H9 | H Sale & close-out | Close-out: final P&L vs appraisal in DealsDash; lessons learned | Paul | Both |  |  | 2 | 2 | N | Y | 2 | H7FS | 0 | 2027-08-09 | 2027-08-10 | Not started |  | Feed actual durations back into this template.
Note on C8: Usually 28 days from the auction — check the special conditions in the legal pack.
Note on C10: Illustrative default. Adds slack to every construction activity marked Contingency = Y.
Note on C12: Illustrative: about 6 weeks. Lengthen if listing in a slow month or stock is high.
Note on C13: From your bridging offer. Compared with months owned in Key Dates.
Note on F5: Built before 2000 → asbestos refurbishment survey before strip-out
Note on F6: Wall removal / lintels / beams → engineer + Building Control
Note on F7: Damp-proofing or timber treatment needed
Note on F8: Roof, gutters, pointing, render (weather-dependent)
Note on F9: Replacement windows / external doors (long lead, FENSA cert)
Note on F10: Full or partial rewire (EIC certificate)
Note on F11: Heating / boiler work (Gas Safe + Building Regs notice)
Note on F12: New kitchen
Note on F13: New bathroom

## Deal 2
VIXIV LTD — Flip programme: Deal 2
Edit only the YELLOW cells (blue text). Dates, Gantt and flags recalculate. Durations are working days. Example values shown — replace with your deal.
| DEAL INPUTS |  |  | SCOPE SWITCHES (Y/N) |  |  | KEY DATES (calculated)
| Deal name / address | EXAMPLE — 3-bed semi via agent (replace) |  | Pre-2000 build | Y |  | Purchase completion | 2027-03-31
| Purchase route | Estate agent |  | Structural | N |  | Works start (strip-out) | 2027-04-08
| Deal secured date | 2027-02-01 |  | Damp/timber | Y |  | Practical completion | 2027-06-25
| Auction completion period (calendar days) | 28 |  | Roof/external | N |  | Listed | 2027-06-30
| Agent route: exchange → completion (WD) | 10 |  | Windows/doors | Y |  | Sale agreed | 2027-08-11
| Contingency on construction durations | 15% |  | Rewire | Y |  | Sale completed | 2027-10-22
| Winter drying allowance (extra WD, Nov–Feb) | 3 |  | Heating/boiler | Y |  | Build duration (WD) | 55
| WD to agree a sale after listing | 30 |  | Kitchen | Y |  | Months owned (completion → sale) | 6.7346
| Bridge term (months) | 12 |  | Bathroom | Y |  | Bridge headroom (months) | 5.2654
| Lead contractor | Friend (general builder) |  |  |  |  | Deal secured → sale completed (days) | 263
| Sale: exchange → completion (WD) | 10
| Gantt key: | A Purchase & DD | B Pre-start | C Strip-out & structure | D First fix | E Plaster | F Second fix & finish | G Sign-off | H Sale & close-out | ■ milestone
[19 empty] | Feb 27 |  |  |  | Mar 27 |  |  |  |  | Apr 27 |  |  |  | May 27 |  |  |  |  | Jun 27 |  |  |  | Jul 27 |  |  |  | Aug 27 |  |  |  |  | Sep 27 |  |  |  | Oct 27 |  |  |  | Nov 27 |  |  |  |  | Dec 27 |  |  |  | Jan 28 |  |  |  |  | Feb 28 |  |  |  | Mar 28
ID | Phase | Activity | Owner | Route | Scope switch | Hold point | Dur WD (auction) | Dur WD (agent) | Contingency? | Applies? | Dur used (WD) | Predecessors | Lag (WD) | Start | Finish | Status | Flags | Notes / what good looks like | time axis 2027-02-01 to 2028-03-20
A1 | A Purchase & DD | Deal secured (auction: hammer falls = exchange; agent: offer accepted) | Paul | Both |  |  | 0 | 0 | N | Y | 0 | — | 0 | 2027-02-01 | 2027-02-01 | Not started |  | Day 0. Everything else is driven from the date in C7.
A2 | A Purchase & DD | Buildings insurance (unoccupied cover) in force | Paul / broker | Both |  |  | 1 | 1 | N | Y | 1 | A1SS | 0 | 2027-02-01 | 2027-02-01 | Not started |  | Auction: risk passes to you at the hammer. Agent route: must be on cover from exchange at the latest.
A3 | A Purchase & DD | Pay 10% deposit + buyer's premium / auction fees | Paul | Auction |  |  | 1 | 0 | N | N | 0 | A1SS | 0 | 2027-02-01 | 2027-01-29 | Not started |  | Paid on the day. Funds must be ready before you bid.
A4 | A Purchase & DD | Instruct solicitor; legal pack / memorandum of sale to solicitor and lender | Paul | Both |  |  | 2 | 2 | N | Y | 2 | A1SS | 0 | 2027-02-01 | 2027-02-02 | Not started
A5 | A Purchase & DD | Bridging valuation instructed and inspection done | Broker / lender | Both |  |  | 5 | 5 | N | Y | 5 | A4SS | 1 | 2027-02-02 | 2027-02-08 | Not started |  | Ideally have a decision in principle BEFORE the auction.
A6 | A Purchase & DD | Bridging underwriting and formal loan offer | Lender | Both |  |  | 5 | 5 | N | Y | 5 | A5FS | 0 | 2027-02-09 | 2027-02-15 | Not started
A7 | A Purchase & DD | Searches and enquiries raised and answered | Solicitor | Estate agent |  |  | 0 | 25 | N | Y | 25 | A4FS | 0 | 2027-02-03 | 2027-03-09 | Not started |  | Auction route: done BEFORE bidding (see DD Checklist).
A8 | A Purchase & DD | Independent survey + builder walk-round for quote | Surveyor / builder | Estate agent |  |  | 0 | 10 | N | Y | 10 | A4SS | 2 | 2027-02-03 | 2027-02-16 | Not started
A9 | A Purchase & DD | Review title, searches and survey: renegotiate or withdraw | Paul + mentor | Estate agent |  | HOLD | 0 | 3 | N | Y | 3 | A7FS; A8FS | 0 | 2027-03-10 | 2027-03-12 | Not started | ■ HOLD: go/no-go. | Re-run the DealsDash appraisal with real costs. Walk away if it fails.
A10 | A Purchase & DD | Exchange contracts (deposit paid) | Solicitor | Estate agent |  |  | 0 | 0 | N | Y | 0 | A9FS; A6FS | 0 | 2027-03-15 | 2027-03-15 | Not started |  | Legally committed from here.
A11 | A Purchase & DD | Lender's legal work, report on title, funds requested | Solicitors | Both |  |  | 5 | 5 | N | Y | 5 | A6FS; A10FS | 0 | 2027-03-16 | 2027-03-22 | Not started
A12 | A Purchase & DD | PURCHASE COMPLETION: keys released | Solicitor | Both |  |  | 0 | 0 | N | Y | 0 | A1 (auction) / A10, A11 (agent) | 0 | 2027-03-31 | 2027-03-31 | Not started |  | Auction: fixed by contract (usually 28 calendar days). Agent: exchange + C9 working days.
B1 | B Pre-start | Builder schedule of works and measured scope | Builder | Both |  |  | 3 | 3 | N | Y | 3 | A1FS; A8FS | 0 | 2027-02-17 | 2027-02-19 | Not started |  | Auction: arrange access via auctioneer/seller, or use the pre-bid viewing scope.
B2 | B Pre-start | Fixed-price quote(s) received; mentor review | Builder / mentor | Both |  |  | 5 | 5 | N | Y | 5 | B1FS | 0 | 2027-02-22 | 2027-02-26 | Not started
B3 | B Pre-start | Sign contract: scope, stage payments, 5% retention; check insurance, verify CIS | Paul | Both |  | HOLD | 2 | 2 | N | Y | 2 | B2FS | 0 | 2027-03-01 | 2027-03-02 | Not started | ■ HOLD: go/no-go. | No signed scope + price = no start.
B4 | B Pre-start | Order long-lead items (kitchen, boiler, windows) | Paul / builder | Both |  |  | 1 | 1 | N | Y | 1 | B3FS | 0 | 2027-03-03 | 2027-03-03 | Not started
B5 | B Pre-start | Long-lead delivery window | Suppliers | Both |  |  | 15 | 15 | N | Y | 15 | B4FS | 0 | 2027-03-04 | 2027-03-24 | Not started |  | Typical 3 weeks; windows can be 4–6. Edit to supplier quote.
B6 | B Pre-start | Asbestos refurbishment survey | Surveyor | Both | Pre-2000 build |  | 5 | 5 | N | Y | 5 | A12FS | 0 | 2027-04-01 | 2027-04-07 | Not started |  | Before any intrusive work on a pre-2000 property (HSE guidance — confirm with contractor).
B7 | B Pre-start | Utilities and meter readings, council tax, change locks, skip, start photos | Paul | Both |  |  | 1 | 1 | N | Y | 1 | A12FS | 0 | 2027-04-01 | 2027-04-01 | Not started
C1 | C Strip-out & structure | Strip-out: kitchen, bathroom, flooring, blown plaster | Builder | Both |  |  | 4 | 4 | Y | Y | 5 | B7FS; B6FS; B3FS | 0 | 2027-04-08 | 2027-04-14 | Not started
C2 | C Strip-out & structure | Opening-up inspection; update costs in DealsDash | Paul + builder | Both |  | HOLD | 1 | 1 | N | Y | 1 | C1FS | 0 | 2027-04-15 | 2027-04-15 | Not started | ■ HOLD: go/no-go. | Hidden defects show here. Re-check profit vs target before committing more spend.
C3 | C Strip-out & structure | Structural works (engineer design + Building Control notice) | Builder / engineer | Both | Structural |  | 5 | 5 | Y | N | 0 | C2FS | 0 | 2027-04-16 | 2027-04-15 | Not started
C4 | C Strip-out & structure | Damp-proofing / timber treatment | Specialist | Both | Damp/timber |  | 3 | 3 | Y | Y | 4 | C2FS | 0 | 2027-04-16 | 2027-04-21 | Not started |  | Get the guarantee for the sale pack.
C5 | C Strip-out & structure | Roof and external repairs (roof, gutters, pointing, render) | Roofer / builder | Both | Roof/external |  | 8 | 8 | Y | N | 0 | C2FS | 0 | 2027-04-16 | 2027-04-15 | Not started
C6 | C Strip-out & structure | Windows and external doors fitted | Installer | Both | Windows/doors |  | 3 | 3 | Y | Y | 4 | C2FS; B5FS | 0 | 2027-04-16 | 2027-04-21 | Not started |  | Keep FENSA certificate.
D1 | D First fix | Electrical first fix (rewire) | Electrician | Both | Rewire |  | 4 | 4 | Y | Y | 5 | C3FS; C4FS | 0 | 2027-04-22 | 2027-04-28 | Not started
D2 | D First fix | Plumbing and heating first fix | Plumber | Both | Heating/boiler |  | 4 | 4 | Y | Y | 5 | C3FS; C4FS | 1 | 2027-04-23 | 2027-04-29 | Not started |  | Starts 1 day after electrics to share the site.
D3 | D First fix | Joinery first fix (stud walls, linings) | Carpenter | Both |  |  | 3 | 3 | Y | Y | 4 | C3FS; C4FS | 0 | 2027-04-22 | 2027-04-27 | Not started
D4 | D First fix | First-fix check before boarding (electrician / Building Control if notifiable) | Builder | Both |  | HOLD | 1 | 1 | N | Y | 1 | D1FS; D2FS; D3FS | 0 | 2027-04-30 | 2027-04-30 | Not started | ■ HOLD: go/no-go. | Photograph every wall before boarding.
E1 | E Plaster | Board, plaster and skim | Plasterer | Both |  |  | 6 | 6 | Y | Y | 7 | D4FS; C5FS; C6FS | 0 | 2027-05-04 | 2027-05-12 | Not started |  | Roof watertight and windows in first.
E2 | E Plaster | Drying out (winter allowance added automatically Nov–Feb) | — | Both |  |  | 5 | 5 | N | Y | 5 | E1FS | 0 | 2027-05-13 | 2027-05-19 | Not started |  | Heat + dehumidifiers. Painting too early = cracking and bloom.
E3 | E Plaster | Mist coat | Decorator | Both |  |  | 2 | 2 | Y | Y | 3 | E2FS | 0 | 2027-05-20 | 2027-05-24 | Not started
F1 | F Second fix & finish | Kitchen fit | Kitchen fitter | Both | Kitchen |  | 4 | 4 | Y | Y | 5 | E3FS; B5FS | 0 | 2027-05-25 | 2027-06-01 | Not started
F2 | F Second fix & finish | Bathroom fit and tiling | Plumber / tiler | Both | Bathroom |  | 5 | 5 | Y | Y | 6 | E3FS | 0 | 2027-05-25 | 2027-06-02 | Not started
F3 | F Second fix & finish | Electrical second fix and testing | Electrician | Both |  |  | 2 | 2 | Y | Y | 3 | F1FS; F2FS | 0 | 2027-06-03 | 2027-06-07 | Not started
F4 | F Second fix & finish | Plumbing / heating second fix; boiler commissioned | Plumber / Gas Safe | Both |  |  | 2 | 2 | Y | Y | 3 | F1FS; F2FS | 0 | 2027-06-03 | 2027-06-07 | Not started
F5 | F Second fix & finish | Joinery second fix (doors, skirting, architrave) | Carpenter | Both |  |  | 3 | 3 | Y | Y | 4 | E3FS | 0 | 2027-05-25 | 2027-05-28 | Not started
F6 | F Second fix & finish | Decoration | Decorator | Both |  |  | 6 | 6 | Y | Y | 7 | F3FS; F4FS; F5FS | 0 | 2027-06-08 | 2027-06-16 | Not started
F7 | F Second fix & finish | Flooring | Flooring fitter | Both |  |  | 2 | 2 | Y | Y | 3 | F6FS | 0 | 2027-06-17 | 2027-06-21 | Not started
F8 | F Second fix & finish | Kerb appeal: front door, paint, garden tidy | Builder | Both |  |  | 2 | 2 | Y | Y | 3 | F6FS | 0 | 2027-06-17 | 2027-06-21 | Not started |  | Training rule: £1 of refurb should add £3 of value.
G1 | G Sign-off | Certificates: EIC (Part P), Gas Safe / Building Regs, FENSA, Building Control completion | Trades | Both |  |  | 3 | 3 | N | Y | 3 | F3FS; F4FS | 0 | 2027-06-08 | 2027-06-10 | Not started |  | Buyer's solicitor will ask for every one. No certs = delayed exchange.
G2 | G Sign-off | Snagging walk-round and fixes | Paul + builder | Both |  |  | 3 | 3 | N | Y | 3 | F7FS; F8FS | 0 | 2027-06-22 | 2027-06-24 | Not started
G3 | G Sign-off | PRACTICAL COMPLETION: stage payment (5% retention held) | Paul | Both |  | HOLD | 0 | 0 | N | Y | 0 | G2FS | 0 | 2027-06-25 | 2027-06-25 | Not started | ■ HOLD: go/no-go. | Sign off only when the snag list is clear.
G4 | G Sign-off | EPC commissioned | Assessor | Both |  |  | 2 | 2 | N | Y | 2 | G2FS | 0 | 2027-06-25 | 2027-06-28 | Not started |  | Must be commissioned before marketing.
G5 | G Sign-off | Deep clean, staging, photos and floorplan | Paul | Both |  |  | 3 | 3 | N | Y | 3 | G2FS | 0 | 2027-06-25 | 2027-06-29 | Not started
H1 | H Sale & close-out | Three agent valuations; instruct agent | Paul | Both |  |  | 3 | 3 | N | Y | 3 | G2SS | 0 | 2027-06-22 | 2027-06-24 | Not started |  | Book during snagging.
H2 | H Sale & close-out | LISTED on portals | Agent | Both |  |  | 0 | 0 | N | Y | 0 | H1FS; G4FS; G5FS | 0 | 2027-06-30 | 2027-06-30 | Not started
H3 | H Sale & close-out | Viewings → sale agreed | Agent | Both |  |  | 30 | 30 | N | Y | 30 | H2FS | 0 | 2027-07-01 | 2027-08-11 | Not started |  | Duration set in C12.
H4 | H Sale & close-out | Memorandum of sale; buyer's mortgage valuation | Agent / buyer | Both |  |  | 10 | 10 | N | Y | 10 | H3FS | 0 | 2027-08-12 | 2027-08-25 | Not started
H5 | H Sale & close-out | Buyer's searches, enquiries and survey; supply certificates | Solicitors | Both |  |  | 40 | 40 | N | Y | 40 | H3FS | 0 | 2027-08-12 | 2027-10-07 | Not started |  | Chase weekly. Typical sale-agreed → completion: 12–16 weeks.
H6 | H Sale & close-out | Exchange contracts on sale | Solicitors | Both |  |  | 0 | 0 | N | Y | 0 | H4FS; H5FS; G1FS | 0 | 2027-10-08 | 2027-10-08 | Not started
H7 | H Sale & close-out | SALE COMPLETION: bridge redeemed | Solicitor | Both |  |  | 0 | 0 | N | Y | 0 | H6FS | 9 | 2027-10-22 | 2027-10-22 | Not started |  | Lag = C15 − 1 so completion lands C15 working days after exchange.
H8 | H Sale & close-out | Retention released (end of defects period) | Paul | Both |  |  | 0 | 0 | N | Y | 0 | G3FS | 60 | 2027-09-21 | 2027-09-21 | Not started |  | Lag 60 WD ≈ 3 months after practical completion.
H9 | H Sale & close-out | Close-out: final P&L vs appraisal in DealsDash; lessons learned | Paul | Both |  |  | 2 | 2 | N | Y | 2 | H7FS | 0 | 2027-10-25 | 2027-10-26 | Not started |  | Feed actual durations back into this template.
Note on C8: Usually 28 days from the auction — check the special conditions in the legal pack.
Note on C10: Illustrative default. Adds slack to every construction activity marked Contingency = Y.
Note on C12: Illustrative: about 6 weeks. Lengthen if listing in a slow month or stock is high.
Note on C13: From your bridging offer. Compared with months owned in Key Dates.
Note on F5: Built before 2000 → asbestos refurbishment survey before strip-out
Note on F6: Wall removal / lintels / beams → engineer + Building Control
Note on F7: Damp-proofing or timber treatment needed
Note on F8: Roof, gutters, pointing, render (weather-dependent)
Note on F9: Replacement windows / external doors (long lead, FENSA cert)
Note on F10: Full or partial rewire (EIC certificate)
Note on F11: Heating / boiler work (Gas Safe + Building Regs notice)
Note on F12: New kitchen
Note on F13: New bathroom

## Holidays
Non-working days used by every date formula
England & Wales bank holidays computed for 2026–2028 — verify at gov.uk/bank-holidays. Trade shutdown days are editable; add your own (e.g. crew holidays) in the yellow rows.
Description | Date
Christmas / Boxing Day (substitute if weekend) | 2026-12-25
Christmas / Boxing Day (substitute if weekend) | 2026-12-28
Trade Christmas shutdown (editable) | 2026-12-29
Trade Christmas shutdown (editable) | 2026-12-30
Trade Christmas shutdown (editable) | 2026-12-31
New Year's Day | 2027-01-01
Good Friday | 2027-03-26
Easter Monday | 2027-03-29
Early May bank holiday | 2027-05-03
Spring bank holiday | 2027-05-31
Summer bank holiday | 2027-08-30
Christmas / Boxing Day (substitute if weekend) | 2027-12-27
Christmas / Boxing Day (substitute if weekend) | 2027-12-28
Trade Christmas shutdown (editable) | 2027-12-29
Trade Christmas shutdown (editable) | 2027-12-30
Trade Christmas shutdown (editable) | 2027-12-31
New Year's Day | 2028-01-03
Good Friday | 2028-04-14
Easter Monday | 2028-04-17
Early May bank holiday | 2028-05-01
Spring bank holiday | 2028-05-29
Summer bank holiday | 2028-08-28
Christmas / Boxing Day (substitute if weekend) | 2028-12-25
Christmas / Boxing Day (substitute if weekend) | 2028-12-26